## Question
Note on A1: John Bryson from YouTube: Hi, I am a real estate agent and for the life of me I can't figure out how to create a computation of time spreadsheet. For example, If I have a buyer that has an offer accepted, this begins a time frame for when he has to have his inspection completed by. So, in this example, he has 10 days. What I would like is a spread sheet where I can put in the date that the offer is accepted, and have all of the timeline due dates shown. Does that make sense? Can you help me? Thanks, John

## Try
Note on A1: John Bryson from YouTube: Hi, I am a real estate agent and for the life of me I can't figure out how to create a computation of time spreadsheet. For example, If I have a buyer that has an offer accepted, this begins a time frame for when he has to have his inspection completed by. So, in this example, he has 10 days. What I would like is a spread sheet where I can put in the date that the offer is accepted, and have all of the timeline due dates shown. Does that make sense? Can you help me? Thanks, John

## MrExcel
Events Table
[8 empty] | Event | Description | # of Days | After
[8 empty] | A | Offer Acceptance | - | -
[8 empty] | B | Inspection Done | 10 | A
[8 empty] | C | Title Search Done | 7 | B
[8 empty] | D | Financing Approved | 25 | A
[8 empty] | E | Closing | 5 | D
[8 empty] | F | Deed Filing | 3 | E
[8 empty] | G | Event 7 | 31 | A
[8 empty] | H | Event 8 | 12 | G
[8 empty] | I | Event 9 | 3 | H
Event | Description | Forecast Date | Actual Date | Date to Use | Predecessor | Pred. Date | Delay | Holiday Table
A | Offer Acceptance |  | 2014-11-21 | 2014-11-21 |  |  |  | 2014-11-27
B | Inspection Done | 2014-12-08 | 2014-12-05 | 2014-12-05 | A | 2014-11-21 | 10 | 2014-12-25
C | Title Search Done | 2014-12-16 |  | 2014-12-16 | B | 2014-12-05 | 7 | 2015-01-01
D | Financing Approved | 2014-12-30 |  | 2014-12-30 | A | 2014-11-21 | 25 | 2015-01-19
E | Closing | 2015-01-07 |  | 2015-01-07 | D | 2014-12-30 | 5 | 2015-02-16
F | Deed Filing | 2015-01-12 |  | 2015-01-12 | E | 2015-01-07 | 3 | 2015-05-25
G | Event 7 | 2015-01-08 |  | 2015-01-08 | A | 2014-11-21 | 31 | 2015-07-03
H | Event 8 | 2015-01-27 |  | 2015-01-27 | G | 2015-01-08 | 12 | 2015-09-07
I | Event 9 | 2015-01-30 |  | 2015-01-30 | H | 2015-01-27 | 3 | 2015-10-12
2015-11-11
2015-11-26
2015-12-25
Formulas:
Date to Use = HLOOKUP(99999999,[Forecast Date]:[Actual Date],1,TRUE)
Forecast Date = WORKDAY([Pred. Date],[Delay],L16:L27)
Pred. Date = VLOOKUP([Predecessor],B16:F24,5,0)

## excelisfun
A | Offer Acceptance | - | -
B | Inspection Done | 10 | A
C | Title Search Done | 7 | B
D | Financing Approved | 25 | A
E | Closing | 5 | D
F | Deed Filing | 3 | E
G | Event 7 | 31 | A
H | Event 8 | 12 | G
I | Event 9 | 3 | H
| Offer Accepted | 2014-11-26 | [7 empty] | Holiday Table
| Days | 15 | [7 empty] | 2014-11-27
2014-12-25
|  | Dates |  | Key | Previous Key | Category | long way | Regular Days | Weekday | 2015-01-01
|  | 2014-11-26 |  | A | - | Offer Acceptance | 2014-11-26 | 2014-11-26 | 2014-11-26 | 2015-01-19
|  | 2014-11-27 |  | B | A | Inspection Done | 2014-12-06 | 2014-12-06 | 2014-12-11 | 2015-02-16
|  | 2014-11-28 |  | C | B | Title Search Done | 2014-12-13 | 2014-12-13 | 2014-12-22 | 2015-05-25
|  | 2014-11-29 |  | D | A | Financing Approved | 2014-12-21 | 2014-12-21 | 2015-01-05 | 2015-07-03
|  | 2014-11-30 |  | E | D | Closing | 2014-12-26 | 2014-12-26 | 2015-01-12 | 2015-09-07
|  | 2014-12-01 |  | F | E | Deed Filing | 2014-12-29 | 2014-12-29 | 2015-01-15 | 2015-10-12
|  | 2014-12-02 |  | G | A | Event 7 | 2014-12-27 | 2014-12-27 | 2015-01-13 | 2015-11-11
|  | 2014-12-03 |  | H | G | Event 8 | 2015-01-08 | 2015-01-08 | 2015-01-30 | 2015-11-26
|  | 2014-12-04 |  | I | H | Event 9 | 2015-01-11 | 2015-01-11 | 2015-02-04 | 2015-12-25
2014-12-05
2014-12-06
2014-12-07
2014-12-08
2014-12-09
Formulas:
Dates = IF(AND(COUNT(C13:C14)=2,ROWS(C17:[Dates])<C14),C13+ROWS(C17:[Dates])-1,"")
long way = [Regular Days]
long way = [long way, row above]+C4
Regular Days = VLOOKUP([Previous Key],E17:[Regular Days, row above],5)+VLOOKUP([Key],A3:C11,3)
Weekday = [long way]
Weekday = WORKDAY.INTL(VLOOKUP([Previous Key],E17:[Weekday, row above],6),VLOOKUP([Key],A3:C11,3),1,L14:L25)
Note on A1: John Bryson from YouTube: Hi, I am a real estate agent and for the life of me I can't figure out how to create a computation of time spreadsheet. For example, If I have a buyer that has an offer accepted, this begins a time frame for when he has to have his inspection completed by. So, in this example, he has 10 days. What I would like is a spread sheet where I can put in the date that the offer is accepted, and have all of the timeline due dates shown. Does that make sense? Can you help me? Thanks, John